**BRIEFING REGARDING “PROVISION OF SOLID WASTE MACHINERY & EQUIPMENT FOR SOLID WASTE MANAGEMENT IN WAZIRABAD CITY” UNDER PUNJAB CITIES PROGRAM (PCP) UNIT WAZIRABAD DISTRICT COUNCIL GUJRANWALA.**

* The PC-I for Solid Waste Machinery and Equipments (which include Vehicle Chassis, Superstructure, Human Recourses, Tracking System) was approved by Local Planning Board (LPB), Gujranwala vide No. 4/28-PB/DD(Dev)/GRW/2021/

3777-84 dated 05-06-2021.

* The Administrative Approval for the said project was issued by the Commissioner Gujranwala Division vide No. Dir(D&F)/GRW/3887 dated 12-08-2021 amounting to Rs. 174.337 (Million).
* Technical sanction for the PC-I/detailed estimate of the above project was approved by Chief Engineer (North), Punjab Local Govt. Board, Lahore vide No. CE(NORTH)PLGB-PS(11)/2021 dated 03-11-2021.
* Subsequent to technical sanction of PC-I, purchase orders for vehicle chassis were issued.
* Details of orders placed for vehicle chassis from local original manufacturers are mentioned in the table below.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No** | **Vehicle Chassis** | **QTY** | **Name of Manufacturer** | **Type of Superstructure to be Built** | **Pre-Receipted Bill Date** | **Purchase Order Issue Date** | **Cheque Amount (Rs.)** | **Delivery Status** |
| 1 | Suzuki Ravi for Mini Tipper 1m3  | 12 | Pak Suzuki Motors | Mini Tipper 1m3  | 03.12.2021 | 21.12.2021 | 1,34,04,000/- | Last week of December 2021 |
| 2 | Tractor for Trollies (50 HP) | 4 | Millat Tractors Limited | Trollies | 15.11.2021 | 24.11.2021 | 9,880,500/- | Last week of December 2021 |
| 3 | Tractor for Mechanical Sweeper (50 HP) | 1 | Millat Tractors Limited | Mechanical Sweeper  | 15.11.2021 | 24.11.2021 |
| 4 | Tractor for Blade 4WD (85 HP) | 1 | Millat Tractors Limited | Front Blade | 15.11.2021 | 24.11.2021 |
| 5 | Tractor for Front End Loader 4WD (85 HP) | 1 | Millat Tractors Limited | Front End Loader | 15.11.2021 | 24.11.2021 |
| 6 | Arm roll Truck 5m3 | 6 | Hinopak Motors | Arm roll 5m3 | 06.12.2021 | 30.12.2021 | 366,000,00/- | 2ndweek of May 2022 |
| 7 | Motorcycle 70 CC | 4 | Atlas Honda | - | 07.12.2021 | 21.12.2021 | 3,79,600/- | 1st week of January 2022 |

* Tenders for the Fabrication of Superstructure on Vehicle Chassis were advertised & published in Newspaper dated 23.12.2021, with last date of submission of Bids & opening on the same date as 11.01.2022, under single stage, Two Envelope procedure.
* Advertisement / tender was cancelled as no bid was received.
* Tenders for the Fabrication of Superstructure on Vehicle Chassis were re-advertised & Published in Newspaper dated 19.01.2022, with last date of submission of Bids & opening on the same date as 08.02.2022, under single stage, Two Envelope procedure.
* Three (03) bidders namely M/S Bilal Engineering Co, M/S Kissan Engineering (Pvt) Ltd & M/S Sumico Technologies (Pvt) Ltd submitted their bidding documents.

Tendering status of superstructure.

* Date of re-advertisement 19-01-2022
* Date of technical bid opening 08-02-2022
* Date of financial bid 28-03-2022
* Date acceptance letter/letter of award 16-04-2022
* Bank guarantee/performance security has been submitted by successful bidder i.e. M/S Bilal Engineering Company (BECO) dated 10-05-2022. Fabrication of superstructure on vehicle chassis is in progress.
* Advertisement for hiring of HR was published in newspaper on 30-4-2022 with last date of submission of applications as 14-05-2022. Scrutiny of applications is in progress.
* Bids for vehicle tracking & Monitoring system & Handcarts conventional have been done. Financial bids will be opened on fixed date & time.
* Pre-qualification documents of contractors have been received dated 1-07-2022, for priority roads & parking shed. Technical Evaluation of contractors (3-Nos) is in process.